| 09.27.26 |  | # Project Status Report |
| --- | --- | --- |

Project Name

TagForge

Course

SDEV-435 Applied Software Practice I

Prepared By

Chris Lynch

Snapshot of Project Activities

| Activity | % Complete | Issues |
| --- | --- | --- |
| 2. Domain model & SQLite database | 60% | Constraints in place; DataType lookup seeded. |
| 3. Flask API & service layer | 17% | Write path not started. |
| 4. NiceGUI user interface | 15% |  |
| 1. Requirements, scope & planning | 75% |  |

# Status Summary

Week 2 moved from design into code. The SQLite schema was created from the week 1 model with foreign keys enforced at runtime, scoped UNIQUE constraints on tag and controller names, and CHECK constraints on the scaling fields, so the last line of data-quality defense now sits in the database rather than only in application code. The DataType lookup is seeded at first run. The repository layer skeleton is in place with the first read endpoint returning tag records, and the Tag Browser and Tag Editor screens now render against that endpoint instead of static markup. No write path yet, and filters are still unwired. Hours this week: 12.00. Cumulative: 24.00 of 100.00.

# Risks Identified / Plan to Mitigate

Scope expansion — unchanged and still primary. No features were added this week; two ideas raised during development, tag-list comparison and duplicate detection across controllers, went to the backlog rather than the schedule. Schedule and budget — unchanged and still open. 24.00 hours consumed over two weeks against a 100-hour budget with 10 weeks remaining.

# Weekly Timesheet

| Activity | Actual Hours Worked |  |  |  |  |  |  |  | Estimated |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Mon | Tues | Wed | Thu | Fri | Sat | Sun | TOTAL | Hours | Date |
|  |  |  |  |  |  |  |  |  | Remaining | Complete |
| 1. Requirements, scope & planning |  |  |  |  |  |  |  | 0.00 | 2.00 | 10/04/26 |
| 2. Domain model & SQLite database | 2.00 | 1.50 |  |  |  | 1.50 |  | 5.00 | 3.00 | 10/11/26 |
| 3. Flask API & service layer |  |  | 1.50 | 1.50 |  |  |  | 3.00 | 15.00 | 10/25/26 |
| 4. NiceGUI user interface |  |  |  |  |  | 1.50 | 2.50 | 4.00 | 14.00 | 11/08/26 |
| 5. Validation & CSV import/export |  |  |  |  |  |  |  | 0.00 | 16.00 | 11/15/26 |
| 6. Testing, integration & defects |  |  |  |  |  |  |  | 0.00 | 14.00 | 11/29/26 |
| 7. Deployment, docs & walkthrough |  |  |  |  |  |  |  | 0.00 | 12.00 | 12/06/26 |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
| Totals: | 2.00 | 1.50 | 1.50 | 1.50 | 0.00 | 3.00 | 2.50 | 12.00 |  |  |