| 10.06.26 |  | # Project Status Report |
| --- | --- | --- |

Project Name

TagForge

Course

SDEV-435 Applied Software Practice I

Prepared By

Chris Lynch

Snapshot of Project Activities

| Activity | % Complete | Issues |
| --- | --- | --- |
| 1. Requirements, scope & planning | 100% | Complete at estimate. M1 passed; design document approved 09/30. |
| 2. Domain model & SQLite database | 100% | Complete at estimate. Migration and seed script build the database from empty. |
| 3. Flask API & service layer | 25% | Update and delete endpoints not written. |
| 4. NiceGUI user interface | 35% | Editor still read-only. |

# Status Summary

The API write path is open — a tag can be created through the service layer, committed, and read back — but update and delete endpoints are not written. In the interface, the Tag Browser filters now call the API instead of filtering a local list, so the status-tile counts reflect what the database returns. Hours this week: 7.50. Cumulative: 31.50 of 100.00. Remaining: 68.50. The pace was cut from 12.00 to 7.50 hours this week to bring the project back inside the 100-hour budget, as flagged in weeks 1 and 2. The remaining 68.50 hours over 9 weeks require 7.5 per week.

# Risks Identified / Plan to Mitigate

Scope expansion — primary risk, unchanged. Nothing was added to the schedule this week. Schedule and budget — closed. The pace was cut from 12.00 to 7.50 hours per week from this week, and the project now tracks to finish inside 100 hours. Validation drift — open, and now under testing.

# Weekly Timesheet

| Activity | Actual Hours Worked |  |  |  |  |  |  |  | Estimated |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Mon | Tues | Wed | Thu | Fri | Sat | Sun | TOTAL | Hours | Date |
|  |  |  |  |  |  |  |  |  | Remaining | Complete |
| 1. Requirements, scope & planning | 1.00 | 1.00 |  |  |  |  |  | 2.00 | 0.00 | 10/04/26 |
| 2. Domain model & SQLite database |  |  | 1.00 | 1.00 |  | 1.00 |  | 3.00 | 0.00 | 10/04/26 |
| 3. Flask API & service layer |  |  |  |  |  | 1.00 | 0.50 | 1.50 | 13.50 | 10/25/26 |
| 4. NiceGUI user interface |  |  |  |  |  |  | 1.00 | 1.00 | 13.00 | 11/08/26 |
| 5. Validation & CSV import/export |  |  |  |  |  |  |  | 0.00 | 16.00 | 11/15/26 |
| 6. Testing, integration & defects |  |  |  |  |  |  |  | 0.00 | 14.00 | 11/29/26 |
| 7. Deployment, docs & walkthrough |  |  |  |  |  |  |  | 0.00 | 12.00 | 12/06/26 |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
| Totals: | 1.00 | 1.00 | 1.00 | 1.00 | 0.00 | 2.00 | 1.50 | 7.50 |  |  |