| 10.11.26 |  | # Project Status Report |
| --- | --- | --- |

Project Name

TagForge

Course

SDEV-435 Applied Software Practice I

Prepared By

Chris Lynch

Snapshot of Project Activities

| Activity | % Complete | Issues |
| --- | --- | --- |
| 3. Flask API & service layer | 47% | Update and delete endpoints still need to be written. |
| 4. NiceGUI user interface | 45% | Editor is still read-only; free-text search is not connected. |
| 5. Validation & CSV import/export | 6% | Validation rules are complete; CSV import has not been started. |
| 7. Deployment, docs & walkthrough | 4% | Repository is published; walkthrough has not been started. |

# Status Summary

This week I worked on connecting the database, API, and user interface. All eight validation rules are now in one module so the editor and API use the same rules and error messages. The repository layer handles the SQL, and the service layer checks the data before saving it. The Flask API can retrieve records and handle POST /api/tags and /api/tags/check. The Tag Browser and Tag Editor now use data from the API instead of static content. The filters call the API, and the dashboard tiles show actual counts, including saved records that do not meet the current validation rules. The editor checks the rules whenever a value changes, but saving from the editor is not available yet. I also put the project under version control and added a README. I completed most of M2, but free-text search still needs to be connected. The basic test creates a new database, saves a tag, closes and reopens the file, and retrieves the saved record. It also checks all eight validation rules and confirms that rejected data is not saved. I worked 7.50 hours this week, bringing the total to 39.00 of the planned 100.00 hours. That leaves 61.00 hours over the remaining 8 weeks.

# Risks Identified / Plan to Mitigate

M2 delay: Four of the five acceptance criteria pass. Free-text search is the remaining item because it is not connected to the API yet. I estimate this will take 3.00 hours to add a search parameter to the tags endpoint and connect the browser's search box. This will be my first task in week 5 so I can finish M2 before the API is finalized at M3. Scope: I did not add any work to the schedule this week. CSV import and report views are still planned for week 7 and later. I am keeping those features on their original schedule so I can finish the current work first. Schedule and hours: I stayed at 7.50 hours this week, the same pace as week 3. With 61.00 hours left over 8 weeks, I need to average about 7.63 hours per week. Two work packages are complete within their estimates, and a third is nearly halfway done. I will review the schedule again at M3 in week 6.

# Weekly Timesheet

| Activity | Actual Hours Worked |  |  |  |  |  |  |  | Estimated |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Mon | Tues | Wed | Thu | Fri | Sat | Sun | TOTAL | Hours | Date |
|  |  |  |  |  |  |  |  |  | Remaining | Complete |
| 1. Requirements, scope & planning |  |  |  |  |  |  |  | 0.00 | 0.00 | 10/04/26 |
| 2. Domain model & SQLite database |  |  |  |  |  |  |  | 0.00 | 0.00 | 10/04/26 |
| 3. Flask API & service layer | 1.00 | 1.50 |  |  |  | 1.50 |  | 4.00 | 9.50 | 10/25/26 |
| 4. NiceGUI user interface |  |  | 1.00 |  |  |  | 1.00 | 2.00 | 11.00 | 11/08/26 |
| 5. Validation & CSV import/export |  |  |  | 1.00 |  |  |  | 1.00 | 15.00 | 11/15/26 |
| 6. Testing, integration & defects |  |  |  |  |  |  |  | 0.00 | 14.00 | 11/29/26 |
| 7. Deployment, docs & walkthrough |  |  |  |  |  | 0.50 |  | 0.50 | 11.50 | 12/06/26 |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
|  |  |  |  |  |  |  |  | 0.00 |  |  |
| Totals: | 1.00 | 1.50 | 1.00 | 1.00 | 0.00 | 2.00 | 1.00 | 7.50 |  |  |